## Sheet1
Project Name | WriteWave
Tested By | Ashish Dadhich
Start Date | 2025-03-14 |  |  |  | Bug Report
End Date | 2025-03-14
Browser/Os | Window10/ Chrome
Proiority | High, Medium, Low
Status | Open
|  | Bug ID | Feature | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot | Comments
|  | BUG-001 | Registration | Verify registration with existing Username | 1.Visit url: https://write-wave-gamma.vercel.app/ 2. Enter already registered username 3. Click Register" | It should be display username already registered. | Its display unknown error | High | High | https://prnt.sc/hiUdMdRnN8Lx | Registration should prevent duplicate usernames.
|  | BUG-002 | Registration | Verify registration with invalid username format | 1.Visit url: https://write-wave-gamma.vercel.app/ 2. Enter invalid username 3. Click Register | It should be display Error message invalid details. | User is successfully register. | Critical | High | https://prnt.sc/IRhZkiNTe5EK | Invalid username format should trigger proper error messages.
|  | BUG-003 | Registration | Verify registration with weak password | 1.Visit url: https://write-wave-gamma.vercel.app/ 2. Enter weak password 3. Click Register | It should be display enter strong and at least 6 character | It display wrong creadential | High | High | https://prnt.sc/4LxlUl9mHqSQ | Weak passwords should be rejected with clear feedback.
|  | BUG-004 | Registration | Verify registration only passing one character password | 1.Visit url: https://write-wave-gamma.vercel.app/ 2. Enter username password 3. Click Register | It should be display error message | Register Sucessffully | Critical | High | https://prnt.sc/R6xGEPWYIVVG | Single-character passwords should not be accepted.
|  | BUG-005 | Registration | Verify registration with password without special characters | 1. Enter valid username & password without special characters 2. Click Register | Error message displayed: "Password must contain special characters" | No validation applied | High | Medium | https://prnt.sc/qKXFJEzXcPXo | Password strength validation is missing for special characters.
|  | BUG-006 | Login | Verify login with empty Fields | 1.Redirected Login page 2.Click Login With empty Fields | It should be display username and password is required. | It display wrong creadentials | High | High | https://prnt.sc/JRjT7OuGCaNl | Empty login fields should trigger a validation error.
|  | BUG-007 | Login | Verify login with non-existent username | 1. Enter a username that is not registered 2. Click Login | Error message displayed: "User does not exist" | Its display only wrong details | High | Medium | https://prnt.sc/Xfe2V91TRQ-3 | Login should return a "User does not exist" message properly.
|  | BUG-008 | Login | Verify password reset with registered username | 1. Enter registered username 2. Click Submit | Password reset link sent | Forget password functionality not available | Critical | High | https://prnt.sc/0yM9a4U-uG99 | Password reset functionality is unavailable for registered users.
|  | BUG-009 | Login | Verify password reset with unregistered Username | 1. Enter unregistered username 2. Click Submit | Error message displayed | Forget password functionality not available | Critical | High | https://prnt.sc/0yM9a4U-uG99 | Unregistered users should receive a clear error for password reset.
|  | BUG-010 | Homepage | Verify navigation bar is functional | 1. Click on each menu item | Navigation should work correctly | All feature redirected to same page | High | High | https://prnt.sc/zMdM_aw6Whk6 | Navigation bar is not working as expected.
|  | BUG-011 | Homepage | Edit and update story | 1.Click on edit story | Story edit and update sucessfully | Functionality Not available | Critical | High | https://prnt.sc/UghmxB70OCPq | Editing and updating stories are non-functional.